## Increment Matrix
Use Case | Use Case Name | Effort (People*Weeks) | Iteration 2* (10/25/18) | Iteration 3* (11/29/18)
UC 1 | Register | 1 | 1 | 0
UC 2 | Login | 0.5 | 0.5 | 0
UC 3 | Logout | 0.5 | 0.5 | 0
UC 4 | Edit Own Profile | 1 | 1 | 0
UC 5 | Edit Another User's Profile | 1 | 1 | 0
UC 6 | Revoke A Renter | 1 | 1 | 0
UC 7 | Request Rental | 2 | 2 | 0
UC 8 | Reserve Selected Rental | 1 | 1 | 0
UC 9 | View My Reserved Rentals | 2 | 2 | 0
UC 10 | Cancel My Reserved Rental | 1 | 1 | 0
UC 11 | View All Rental Reservations | 2 | 2 | 0
UC 12 | View All Available Cars | 2 | 2 | 0
UC 13 | View Rental Reservation Details | 1 | 1 | 0
UC 14 | Delete Rental Reservation | 1 | 1 | 0
|  | Total Effort Estimated | 17 | 0
|  | Total Effort Available (3.25 * teamSize) | 19.5 | 0
|  | Team Size | 6 | 0
* Sum of the effort of each column must not exceed the ability of the team.
* Sum of the efforts of each row must not be less than the required effort.
Note on B1: Functions in black : MUST BE DONE BY IT.2. No argument. Functions in red : Hardest. Might be shifted to IT.3. High chance, but will try best. Functions in blue : Hard functions, might be abandoned in WORST CASE scenario but must be done in It.2 to achieve 85% completion. Try HARDEST to get done. -Arunika Oyshi